| Study Design |  |
| --- | --- |
| Design Type | Randomized, double-blind, placebo-controlled, parallel-group study. |
| # Treatment Arms | 2, active & placebo |
| Randomization Ratio | 1:1 (Active:Placebo) |
| Stratification & distribution assumptions | Body Weight (BW) Strata; Study Distribution; Regional Distribution. <90kg; 76%, n=190; EU: 70 China: 120. >=90kg; 24%, n=60; EU: 30 China: 30. |
| Blinding | Double-blind (patients, investigators, and sponsor blinded) |
| Population |  |
| # Patients | Total: 250 |
| # Countries | 14 |
| # Sites | 100 |
| # Depots | 2 regional/local depots: EU and China |
| #Patients/Regional Depot | EU n=100, China n=150 |
| Treatment Duration |  |
| Patient Duration | 52 weeks |
| Study Duration (1st Subject 1st dose to Last Subject last dose) | need to know to determine if one manufacturing run will support the full study timeline |
| Recruitment Assumptions |  |
| Recruitment duration | 2 years |
| Screening period | 10 days or less |
| %Screen Failures | 35% |
| %Sites who will not actively screen | 15% |
| Dosing & Dispensing Schedule |  |
|  | Dispensing; BW<90kg; BW>90kg. Baseline + Weeks 1-12 (dispense weekly) 13 dispensing events; ACT: 3 kit 3ml PBO: 3 kit 3ml; ACT: 5 kit 5ml PBO: 5 kit 5ml. Weeks 13-52 (dispense every 2 weeks starting at Week 14) 10 dispensing events; ACT: 1 kit 4.5ml PBO: 1 kit 4.5ml; ACT: 1 kit 7.5 ml PBO: 1 kit 7.5ml. |
| At weeks 12 & 24 | Non-responders on ACT arm, continue weekly dosing according to BW for 3 additional weeks before moving to visits every other week. Non-responders on PBO arm, switch to ACT treatment arm according to BW with weekly dosing for 3 weeks then switch to every other week dosing. At week 12 weekly dosing would be Weeks 12, 13, 14. At week 24 weekly dosing would be Weeks 24, 25, 26. |
| Supply Chain Considerations |  |
| Depot Structure |  |
| EU Depot | Supplies 13 countries in Europe and acts as the primary hub |
| China Depot | Supplies China only, but all IP must first ship to EU depot before being forwarded to China depot |
| Shelf Life for Investigational Product (IP) |  |
| From manufacture | 24 months |
| Minimum remaining shelf life for receipt by | EU depot: 6.5 months China: 12 months Sites: 6 months |
| Manufacturing & Release Timelines |  |
| Signal to manufacture | 6 months |
| Time from manufacturing to “ready-to-ship” status (including packaging, labeling, and QA release) | 4 months |
| Lead time (LT) from manufacturing to EU depot | 1 week |
| Lead time (LT) from EU depot to China depot | 2 months |
| Depot-to-site LT | <10 days for all countries |
| Labeling | Same label group for China and EU countries (single multilingual label set) |
| Supply/Re-supply |  |
| Start Up Supply | EU Depot: X months of supply China Depot: Sites: |
| Re-Supply Strategy | Strategy; Logic; Characteristics. UORO; Use 1 → Replace 1; Simple, stable inventory, minimal complexity. Min/Max; Refill when inventory < threshold; Common for medium/large trials. Predictive; Use enrollment forecast to decide resupply; Efficient but algorithmically complex, predictive use over next x time period. Just-in-Time. |
| Stock Out Tolerance % | 5% |
| Manufacturing |  |
| Raw Drug made per manufacturing run | X ml, or kg or tablets etc. |
| Formulation | 1st generation, 2nd generation |
| Dose(s) | 0.375mg / ml |
| Volume | 3ml, 4.5ml, 5ml, 7.5 ml |
| Route of Administration | IV, subcutaneous, intramuscular, intrathecal, inhaled, oral, topical, buccal, etc. |
| Kit types & number needed per type | Table represents maximum expected assuming full enrollment and all patients complete all dispensing visits. Body Weight (BW) Strata; Study Distribution; Depot Distribution. <90kg (n=190); 3ml: 3 kits x 13 dispensing x 190 patients = 7,410 kits; EU: 70pts, 2730 kits China: 120 pts, 4,680 kits. 4.5ml: 1 kit x 10 dispensing x 190 patients = 1900 kits; EU: 70pts, 700 kits China: 120 pts, 12,000 kits. >=90kg (n=60); 5ml: 5 kits x 13 dispensing x 60 patients = 3900 kits; EU: 30 patients, 1950 kits China: 30 patients, 1950 kits. 7.5ml: 1 kit X 10 dispensing X 60 patients = 600 kits; EU: 30 patients, 300 kits China: 30 patients, 300 kits. |
| Costs ($) |  |
| Manufacturing (raw drug supply) costs | Costs for one manufacturing run how many kits can be made from a “standard” raw drug manufacturing run |
| Kit Pack & Label costs | Will all raw drug be packaged and labeled when manufacturing is completed. |
| Cost per shipment (Manufacturing to depot) | #kits/shipment (may vary based on initial supply and resupply strategy) What is the kit storage capacity at the depots? |

Main Components and Weighting

Drug minimization(w1) + Costs(w2) + Stock Out Tolerance(w3)